## ProjectSchedule
DRONES IN CONSTRUCTION - Thesis 2025
UCD Applied Robotics Project |  | Project Start: | 2025-06-15 | [29 empty] | Team Members Legend: | [10 empty] | Ben |  |  |  | John |  |  |  | Stefi |  |  |  | All
Walls Construction |  | Today: | 2025-08-15 | [29 empty] | Task Bar Legend: | [10 empty] | Completed Progress | [9 empty] | Planned Duration
|  | Display Week: | 1
[9 empty] | 2025-06-16 | [6 empty] | 2025-06-23 | [6 empty] | 2025-06-30 | [6 empty] | 2025-07-07 | [6 empty] | 2025-07-14 | [6 empty] | 2025-07-21 | [6 empty] | 2025-07-28 | [6 empty] | 2025-08-04 | [6 empty] | 2025-08-11 | [6 empty] | 2025-08-18 | [6 empty] | 2025-08-25
 | time axis 2025-06-16 to 2025-08-31
TASK | ASSIGNED TO | TASK DESCRIPTION | PRIORITY LEVEL | PROGRESS | START | END | SOURCE MATERIAL | DAYS | time axis 2025-06-16 to 2025-08-31
Phase 1 - Literature Review
Research + Write | John | Industrial UAV Surveying Methods | Medium | 100% | 2025-06-15 | 2025-07-01 | Source | 17
Research + Write | Stefi | GPS-denied Localization | Medium | 100% | 2025-06-15 | 2025-07-01 |  | 17
Research + Write | Ben | BIM integration, Clash Detection | Medium | 100% | 2025-06-15 | 2025-07-01 |  | 17
Review | All | Review, refinement, reference formatting | Medium | 100% | 2025-06-15 | 2025-07-01 |  | 17
Adjustments | All | Implementation of feedback, final review | High | 100% | 2025-05-15 | 2025-07-22 |  | 69
Phase 2 - Qualification Stage
IAA Certification | All | IAA Course Completition | High | 100% | 2025-06-30 | 2025-06-30 |  | 1
Drone Course | All | Data visualisation, drone piloting, modelling | High | 100% | 2025-07-02 | 2025-07-02 |  | 1
Research | All | Waypoint flight generator | High | 100% | 2025-07-07 | 2025-07-17 |  | 11
Marvelmind Sys | All | Donwload, set up, license, research | High | 100% | 2025-07-07 | 2025-07-17 |  | 11
DJI Drone | All | Research DJI Integration | High | 100% | 2025-07-07 | 2025-07-17 |  | 11
Phase 3 - Implementation Stage
Software | Ben | Waypoint generator through Boustrophedon | High | 100% | 2025-07-17 | 2025-07-28 |  | 12
Software | Stefi | Accuracy in battery + flight time required | High | 100% | 2025-07-17 | 2025-07-28 |  | 12
Hardware | John | Beacon Setup + Marvelmind setup | High | 100% | 2025-07-17 | 2025-07-28 |  | 12
Software | All | Revision and refinement code (lawnmower 2D) | High | 100% | 2025-07-28 | 2025-08-01 |  | 5
Software | Stefi | Waypoint generator (geometrical spiral 2D) | High | 100% | 2025-07-28 | 2025-08-01
Software | Stefi | Waypoint generator 2D (lawnmower vs spiral) | High | 100% | 2025-07-28 | 2025-08-01
Hardware | Ben | Calibration of Marvelmind system + dpt file import | High | 100% | 2025-07-28 | 2025-08-01
Phase 4 - 2D Flight Testing
Software | All | Geometrical Spiral pattern (floor) | High | 100% | 2025-08-02 | 2025-08-05 |  | 4
Software | All | Lawnmower pattern (floot) | High | 100% | 2025-08-02 | 2025-08-05 |  | 4
Software + Hardware | All | Testing different scenarios (nr. waypoints, height, area coverages) | High | 100% | 2025-08-02 | 2025-08-05 |  | 4
Software + Hardware | All | Polishing of code (testing of turning rate, accelleration, deceleration, battery consuption) | High | 100% | 2025-08-02 | 2025-08-05 |  | 4
Data processing | All | Logging in data + recordings | High | 100% | 2025-08-02 | 2025-08-05 |  | 4
Phase 5 - Software Testing - Photogrammetry
Data processing | All | PolyCam | Medium | 100% | 2025-07-31 | 2025-08-05 |  | 6
Data processing | Stefi | Metashape | Medium | 100% | 2025-07-31 | 2025-08-05 |  | 6
Data processing | John | Reality Capture | Medium | 100% | 2025-07-31 | 2025-08-05 |  | 6
Phase 6 - Software Testing - NeRF
Data processing | All | PolyCam (Gaussian Splat) | Medium | 100% | 2025-07-31 | 2025-08-05 |  | 6
Data processing | All | Luma AI | Medium | 100% | 2025-07-31 | 2025-08-05 |  | 6
Data processing | John | Instant NGP | Medium | 100% | 2025-07-31 | 2025-08-05
Data processing | John | NeRF Studio | Medium | 100% | 2025-07-31 | 2025-08-05
Phase 7 - Data Processing from Flights
Data processing | Ben | Cleaning Data | High | 100% | 2025-08-05 | 2025-08-16
3D model | All | Choosing set software for NeRF and Photogrammetry | High | 100% | 2025-08-05 | 2025-08-05
Data processing | Ben | Report generator from flight logs | High | 100% | 2025-08-05 | 2025-08-16
Data processing | All | From video to 3D scan (photogrammetry and NeRF) | High | 100% | 2025-08-05 | 2025-08-16
Plotting | Ben | Visualisation of results | High | 100% | 2025-08-05 | 2025-08-16
Phase 8 - 2D Flights Validation
Results | All | Processing data from both strategies and scenarios | High | 100% | 2025-08-03 | 2025-08-06
Assessment (report) | All | Resulting reports for data validation | High | 100% | 2025-08-03 | 2025-08-08
Assessment (3D scan) | All | Processing videos for reconstruction models (photogrammetry and nerf) | High | 100% | 2025-08-03 | 2025-08-06
Conclusions | All | Assessment of best stratefy through data report and reconstruction models | High | 100% | 2025-08-03 | 2025-08-06
Polishing | All | Polishing of code through isolated testing to accurately compute flight time + battery consuption which matches the flights | High | 100% | 2025-08-03 | 2025-08-06
Phase 9 - 3D Flight Testing
Software | Stefi | Stacked Geometrical Spiral pattern | High | 100% | 2025-08-07 | 2025-08-13
Software | All | Different scenario testing (different heights, order, lighting, | High | 100% | 2025-08-07 | 2025-08-13
Software + Hardware | All | Testing different scenarios (nr. waypoints, height, area coverages, gimbal rotations, amount of spirals) | High | 100% | 2025-08-07 | 2025-08-13
Software | Stefi | Building a complete dashboard: allow for flightpath generation through user input + report of fligtt | High | 100% | 2025-08-07 | 2025-08-13
Data processing | Ben | Logging in data + recordings | High | 100% | 2025-08-07 | 2025-08-13
Photogrammetry | All | Processing data for photogrammetry reconstruction | High | 100% | 2025-08-07 | 2025-08-13
NeRF | All | Processing data for NeRF reconstruction | High | 100% | 2025-08-07 | 2025-08-13
CloudCompare | Ben | 3D reconstruction analysis through cloud point analysis | High | 100% | 2025-08-07 | 2025-08-13
Assessment of results | All | Choose best strategy according to anaylsis of results | High | 100% | 2025-08-07 | 2025-08-13
Assessment 3D | Ben | Comparison between Photogrammetry and NeRF | High | 70% | 2025-08-07 | 2025-08-13
Phase 10 - Targeted Flights
Software | Stefi | Build complete dashboard to partition space in order to achieve target flights to specific room location | Medium | 100% | 2025-08-12 | 2025-08-15
Flight Testing | All | Test 3 scenarios | Medium | 50% | 2025-08-15 | 2025-08-15
Assessment | Ben | Assessment of photogrammetry and NeRF scan + flight logs | Medium | 60% | 2025-08-15 | 2025-08-15
Results | All | Assessment and validation of new feature | Medium | 0% | 2025-08-15 | 2025-08-15
Phase 11 - Thesis Report
Writing | All | Framework of thesis +writing up | Medium | 15% | 2025-08-16 | 2025-08-29
Citation and Appendix | All | zotero + material | Medium | 0% | 2025-08-16 | 2025-08-29
Proofread | All |  | Medium | 0% | 2025-08-27 | 2025-08-29
Formulas:
Ben = [Ben, row below]
Note on K7: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.

## SourceMaterial
Source Type | Reference
OneDrive | Research Project-Drones in Construction
Literature Review | Literature Review Material
Marvelmind System
DJI Drone Specs | https://www.dji.com/ie/mini-3/specs

## DropDownMenus (hidden)
Ben | Low
John | Medium
Stefi | High
All